## Data
NPARIH capital works progress, number of new houses and refurbishments, by state and territory, 2008-2017
|  | NSW | Qld | WA | SA | Tas | NT | Aust
2016 | New houses | 263 | 833 | 708 | 239 | 12 | 1214 | 3269
2016 | Refurbishments | 1009 | 1490 | 1561 | 304 | 57 | 2929 | 7350
2017 | New houses | 263 | 934 | 725 | 239 | 12 | 1333 | 3506
2017 | Refurbishments | 1009 | 1490 | 1590 | 318 | 57 | 2929 | 7393
2018 | Target - New houses | 310 | 1141 | 1012 | 241 | 18 | 1456 | 4200
2014 | Target - Refurbishments | 101 | 1216 | 1288 | 206 | 13 | 2052 | 4876

## Description
Measure | 4,200 new houses to be delivered by 2018; 4,800 refurbishments to be delivered by 2014.
short title | Construction and refurbishment of homes
Status | Not on track
Updated | 2017
Desc Body | New housing construction
From 2008 to the end of October 2017, the National Partnership on Remote Housing (NPRH) and National Partnership Agreement for Remote Indigenous Housing (NPARIH) delivered a total of 3,506 new houses against the 2018 COAG target of 4,200.
Each of the jurisdictions that have remained in the NPRH are likely to meet their targets for new builds, with the exception of WA. Nationally, based on current performance, 4,020 new houses are expected to be delivered (Commonwealth of Australia 2017). Nationally, this aspect of the benchmark is not on track to be met.
Refurbishment of houses
From 2008 to the end of October 2017, a total of 7,393 refurbishments were delivered, considerably exceeding the 2014 COAG target of 4800. Nationally and for each jurisdiction, this aspect of the benchmark was met.
Notes | Victoria and Tasmania exited the NPARIH in 2014 and New South Wales in 2015, and are not part of the NPRH. The ACT is not part of the NPRH. Tasmania and NSW exited the National Partnership before completing their respective new build targets.
Totals include dwellings built from Commonwealth Own Purpose Expense funding under NPARIH.
Source | State and Territory governments; Department of the Prime Minister and Cabinet.
References | Commonwealth of Australia (2017), Department of the Prime Minister and Cabinet, Remote Housing Review: A Review of the National Partnership Agreement on Remote Indigenous Housing and the Remote Housing Strategy (2008–2018)